Action Plan – Guidelines for Action for 2027–2029

| No. | Action | Responsible | When | Indicator |
| --- | --- | --- | --- | --- |
| 1. | Analyze researchers' salaries regarding gender and age to check for any discrimination | Human Resources and Payroll Department | January each year for the previous year | Analysis and report |
| 2. | Examine the effectiveness of OTMiR procedures and analyze previous actions, including conclusions from surveys and interviews with researchers | Science and Technology Transfer Department and Human Resources and Payroll Department | 12.2028 | Analysis and report |
| 3. | Conduct a satisfaction survey among researchers | Science and Technology Transfer Department and Human Resources and Payroll Department | 08.2028 | Analysis and report |
| 4. | Assess the effectiveness of scientific activity regarding participation in scientific and research projects | Science and Technology Transfer Department | 03.2028 for 2027, 03.2029 for 2028, 03.2030 for 2029 | Analysis and report |
| 5. | Raise awareness among researchers regarding data protection and cybersecurity regulations | Data Protection Officer | Ongoing task | Number of training sessions |
| 6. | Review researchers' job descriptions and conduct a comparative analysis with employee surveys and interviews | Science and Technology Transfer Department and Human Resources and Payroll Department | 12.2028 | Analysis and report |
| 7. | Analyze and compare the processes of periodic evaluation based on Director’s Order No. 8/2022 with the scientific and technical staff evaluation based on the Order 85/2018 regarding scientific achievements and promotion procedures | Science and Technology Transfer Department and Human Resources and Payroll Department | 12.2028 | Analysis and report |
| 8. | External audit of researchers' achievements before the next evaluation of scientific activities quality | Science and Technology Transfer Department | 2027, 2029 | Analysis and report |
| 9. | Review all procedures regarding researchers in light of the newly approved scientific and clinical strategy | Science and Technology Transfer Department and Human Resources and Payroll Department | After introduction of the strategy for following years | Recommendations regarding procedural changes |
| 12. | Develop the Omega PSIR system and repository of staff publications available in open access | Library, Science and Technology Transfer Department | Continuous process | Number of entered publications and scientific achievements data; number of new modules/features launched annually; number of IMC staff publications available under Creative Commons license per year |
| 14. | Improve working conditions for researchers through the construction of a new building (part of the ongoing scientific and clinical strategy for IMC 2025 and beyond) and purchase of new research equipment | Deputy Technical and Administrative Director Division | Continuous process | Realization of the project of new building according to schedule; number and value of new research equipment |
| 15. | Participation of researchers in specialist trainings, scientific conferences, and HR courses | Human Resources and Payroll Department | Continuous process | Number of researchers participating in trainings |
| 16. | Strengthen researchers’ awareness of career paths and development within the Institute through central communication | PR Department, Science and Technology Transfer Department, Human Resources and Payroll Department, Library | Continuous process | Number and content of communications for researchers |
| 17. | Implementing objectives and actions from the Gender Equality Plan | Science and Technology Transfer Department, Human Resources and Payroll Department | Ongoing task - according to Gender Equality Plan | Gender Equality Plan currently in force at IMC – degree of Action Plan implementation |
| 18. | Digitize travel request applications | Human Resources and Payroll Department | 01.2027 | Implementation of electronic workflow module for travel requests |
| 19. | Scientific staff development through increasing the number of employed researchers – approximately 3 recruitments annually, performed in accordance with OTMR procedure | Human Resources and Payroll Department | Ongoing task | Number of employed researchers |
| 20. | Analyze and update, if necessary, the Institute's Employee Ethics Code with regard to researchers | HR Excellence in Research Commission | 12.2028 | Report and possible update of the Code |
| 21. | Monitor complaints and disciplinary proceedings regarding research and development activities of researchers | Science and Technology Transfer Department, Human Resources and Payroll Department, HR Excellence in Research Commission | 12.2027, 12.2029 | Report |
| 22. | Co-financing of publication costs in prestigious scientific journals | Science and Technology Transfer Department | Ongoing task | Annual number of co-financed publications |